## Wx
PROJECT REPORT
Group | <Team 2>
Week | <05/09/2022-17/09/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Select Project Topic | In Progress | Each member choose a topic and discuss to choose the topic
2 | Project and database analysis | In Progress | user- and manager-level project analysis
3 | Divide the structure of a project | In Progress | Front-end: HTML, CSS, SCSS, JavaScript , Bootstrap. Back-end: Java, Servlet, JSP, MS SQL Server
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Get requirments | NghiaPD, DuyNV
2 | design database and create database | VanNDH | Project topic analysis for DB design and drawing
3 | Design web | DungHQ, HoangDV | Draw the frame of the web and build the basic image for the web
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Get requirments | Pending
2 | Learn API | Pending
3 | Discussion, analysis of ERD diagram. | Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Summarize all functions of web app | Pending | Based on requirements to analyze and select key functions for the application
2 | Design | Pending | UI, DB, MVC
3 | Implement | Pending | code
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | F-Dorm | NghiaPD, DuyNV | Based on the dormitory of the national university, we want to develop a dormitory management application for FPT University.
2 | F-Food | DungHQ, HoangDV | Based on the Circle-K of the national university, we want to develop a food web management application for FPT University.
3 | F-Travel | VanNDH | Based on the traveloka of the national university, we want to develop a travel web management application for FPT University.
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue