## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Login | user and admin login into app by account or google | Complex | Iteration 1 | SE150938 | Phạm Đức Nghĩa | Iteration 1
Logout | user and admin logout app | Simple | Iteration 2 | SE151173 | Nguyễn Đức Hải Văn | Iteration 2
Register | user can sign-up the account | Complex | Iteration 3 | SE150938, SE151394 | Phạm Đức Nghĩa, Nguyễn Văn Duy | Iteration 3
Search | user can search product (by filter) | Medium | Iteration 1 | SE150787 | Đỗ Việt Hoàng | Iteration 1
Buy product | user can buy product that they want | Complex | Iteration 2 | SE151397, SE150787 | Hoàng Quốc Dũng, Đỗ Việt Hoàng | Iteration 2
Pay by Banking | user can choose their payment method that they want | Complex | Iteration 2 | SE151394 | Nguyễn Văn Duy | Iteration 3
CRUD | admin can "create", " view", "update", "delete" products | Medium | Iteration 1 | SE151173 | Nguyễn Đức Hải Văn | Iteration 1
Send mess | send message OTP into their phone number to reset password | Complex | Iteration 3 | SE150787, SE151397 | Hoàng Quốc Dũng, Đỗ Việt Hoàng | Iteration 3